## Project_Summary
Project_ID | Vessel_Class | Customer | Contract_Value_NOK | Baseline_Start | Planned_Delivery | Current_Phase | Currency
P-901-CORVETTE | Fast Missile Patrol Vessel (Composite Sandwich) | Royal Norwegian Navy | 485000000 | 2024-01-15 | 2026-11-30 | Production & Outfitting | NOK
P-902-MINESWEEPER | Mine Countermeasures Vessel (MCMV) | Naval Material Command | 320000000 | 2024-06-01 | 2027-04-15 | Hull Fabrication | NOK

## WBS_Cost_Control
WBS_Code | WBS_Description | Department | Budget_NOK | Actual_Cost_NOK | ETC_NOK | EAC_NOK | SPI | CPI | Hours_Actual
WP-100 | Hull & Composite Superstructure | Production Composite | 125000000 | 132500000 | 18000000 | 150500000 | 0.94 | 0.88 | 42500
WP-200 | Propulsion & Gas Turbine Integration | Mechanical Engineering | 95000000 | 89200000 | 12000000 | 101200000 | 0.98 | 0.96 | 18200
WP-300 | Combat Management System & Radar | Systems Integration | 145000000 | 141800000 | 15500000 | 157300000 | 0.99 | 0.95 | 24600
WP-400 | Electrical & Auxiliary Systems | Electrical Engineering | 42000000 | 38600000 | 4500000 | 43100000 | 1.01 | 0.97 | 14300
WP-500 | Sea Acceptance Trials & Commissioning | Project Management | 38000000 | 14500000 | 26500000 | 41000000 | 0.92 | 0.91 | 6800
WP-900 | Management & Technical Contingency | Project Controlling | 40000000 | 0 | 30000000 | 30000000 | 1 | 1 | 1200

## Milestone_Risk
Milestone_ID | Milestone_Name | Target_Date | Status | Risk_Level | Contingency_Allocation_NOK
M-01 | Composite Hull Moulding Complete | 2024-06-30 | Completed | Low | 0
M-02 | Superstructure Infusion & Bonding | 2024-12-15 | Completed | Medium | 2500000
M-03 | Main Gas Turbine Alignment | 2025-05-20 | Delayed | High | 6000000
M-04 | Harbor Acceptance Test (HAT) | 2025-10-15 | In Progress | High | 8500000
M-05 | Sea Acceptance Trials (SAT) | 2026-06-30 | Planned | Critical | 12000000